## Team1_Estimated_Effort
Task Name: (Dependencies top to bottom) | [8 empty] | Colin | Jayson | Ryan | Ian | Wes | Zach | Total
|  |  | Role | Owner | Estimated | Effort | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual
|  |  |  | (primary owner) (secondary owners) | By Task | Subtotals | By Task | Subtotals | By Task | By Task | By Task | By Task | By Task | By Task
Preliminary &
Parallel Tasks | Architecture |  |  |  |  | 12 |  | 10 | [6 empty] | 12
|  | Design architecture | Project Manager | Zach, Wes | 12 |  | 10 | [5 empty] | 6 | 6 | 12
| Requirements |  |  |  |  | 9 |  | 9 | [6 empty] | 9
|  | Gather | Requirements Engineer | Zach, Wes | 2 |  | 2 | [5 empty] | 1 | 1 | 2
|  | Analyze | Requirements Engineer | Zach, Wes | 4 |  | 4 | [5 empty] | 3 | 1 | 4
|  | Specify | Requirements Engineer | Zach, Wes | 3 |  | 3 | [5 empty] | 2 | 1 | 3
| Documentation |  |  |  |  | 28 |  | 28 | [6 empty] | 28
|  | Project Charter | Project Manager | Wes, Zach | 2 |  | 3 | [5 empty] | 2.5 | 0.5 | 3
|  | Release Plan | Project Manager | Zach, Wes | 2 |  | 3 | [5 empty] | 2 | 1 | 3
|  | Requirements Document | Project Manager, Requirements Engineer | Wes, Zach | 5 |  | 6 | [5 empty] | 5 | 1 | 6
|  | Project Plan | Project Manager, Developers | Wes, Zach | 5 |  | 5 | [5 empty] | 3 | 2 | 5
|  | Architecture Document | Architect | Wes, Zach | 4 |  | 4 | [5 empty] | 1 | 3 | 4
|  | Test Report | Tester | Ryan, Ian | 8 |  | 3 |  | 1.5 |  | 1.5 |  |  |  | 3
|  | User Guide & System Admin Doc | Developers, Requirements Engineer | Colin, Ian | 2 |  | 4 |  | 2 |  |  | 2 |  |  | 4
Coding
Iteration 1: | Development |  |  |  |  | 75 |  | 94 | [6 empty] | 94
|  | Determine technology needs | Developer | Everyone :) | 12 |  | 12 |  | 2 | 2 | 2 | 2 | 2 | 2 | 12
|  | Research and learn new language and environment | Developer | Ryan, Colin, Ian | 20 |  | 24 |  | 6 | 6 | 6 | 6 |  |  | 24
|  | Set up azure | Developer | Zach | 10 |  | 4 | [6 empty] | 4 | 4
|  | Write basic azure code | Developer | Zach | 8 |  | 4 | [6 empty] | 4 | 4
|  | Implement classes | Developer | Jayson | 10 |  | 20 |  | 6 | 4 | 10 |  |  |  | 20
|  | Display SSMS information via asp.net | Developer | Colin, Jayson | 6 |  | 12 |  | 6 | 6 |  |  |  |  | 12
|  | Data processing | Developer | Ryan | 3 |  | 4 |  |  |  | 4 |  |  |  | 4
|  | Database populated | Developer | Ryan | 3 |  | 6 |  |  |  | 6 |  |  |  | 6
|  | Unit Testing | Developer | Ian | 3 |  | 8 |  |  |  |  | 8 |  |  | 8
| Analysis |  |  |  |  | 6 |  | 5 | [6 empty] | 5
|  | System Testing | Tester | Jayson, Ian, Colin | 2 |  | 1.5 |  | 0.5 | 0.5 |  | 0.5 |  |  | 1.5
|  | Bug fix as required | Tester, Developer | Jayson, Ian, Colin | 2 |  | 1.5 |  | 0.5 | 0.5 |  | 0.5 |  |  | 1.5
|  | Evaluate needs for next iteration | Project Manager | Wes, Zach | 2 |  | 2 | [5 empty] | 1 | 1 | 2
Iteration 2: | Design |  |  |  |  | 12 |  | 15 | [6 empty] | 15
|  | Implement any design changes | Project Manager | Zach, Wes | 2 |  | 2 | [5 empty] | 1 | 1 | 2
|  | Risk analysis | Project Manager | Zach | 2 |  | 2 | [6 empty] | 2 | 2
|  | Implement cloud SQL server | Project Manager | Zach | 1 |  | 3 | [6 empty] | 3 | 3
|  | Notification rules | Developer | Ryan | 5 |  | 5 | [6 empty] | 5 | 5
|  | UI elements | Developer | Ryan, Wes, Zach | 2 |  | 3 |  |  |  | 1 |  | 1 | 1 | 3
| Development |  |  |  |  | 35 |  | 36 | [6 empty] | 36
|  | Review requirements | Developer | Zach, Wes | 1 |  | 1 | [5 empty] | 0.5 | 0.5 | 1
|  | Implement notifications | Developer | Colin, Jayson | 10 |  | 11 |  | 5.5 | 5.5 |  |  |  |  | 11
|  | Implement additional unit testing | Developer | Ian | 10 |  | 11 | [6 empty] | 11 | 11
|  | Implement basic UI elements | Developer | Ryan | 4 |  | 3 | [6 empty] | 3 | 3
|  | Github security analysis | Developer | Zach | 5 |  | 5 | [6 empty] | 5 | 5
|  | Dashboard Research / Implementation | Developer | Wes | 5 |  | 5 | [6 empty] | 5 | 5
| Analysis |  |  |  |  | 6 |  | 5.5 | [6 empty] | 4.5
|  | System Testing | Tester | Ian, Colin, Jayson | 2 |  | 1.5 |  | 0.5 | 0.5 |  | 0.5 |  |  | 1.5
|  | Bug fix as required | Tester, Developer | Ryan | 2 |  | 2 |  |  |  | 1 |  |  |  | 1
|  | Evaluate needs for next iteration | Project Manager | Zach, Wes | 2 |  | 2 | [5 empty] | 1 | 1 | 2
Iteration 3: | Design |  |  |  |  | 14 |  | 14 | [6 empty] | 14
|  | Implement any design changes | Project Manager | Zach, Ryan | 2 |  | 2 |  |  |  | 1 |  |  | 1 | 2
|  | Risk analysis | Project Manager | Zach, Wes | 2 |  | 2 | [5 empty] | 1 | 1 | 2
|  | Design revised UI | Developer | Zach, Ryan | 6 |  | 6 |  |  |  | 3 |  |  | 3 | 6
|  | Plan security revisions | Developer | Zach | 4 |  | 4 | [6 empty] | 4 | 4
| Development |  |  |  |  | 46 |  | 48 | [6 empty] | 47.75
|  | Build data export feature | Developer | Zach | 4 |  | 4 | [6 empty] | 4 | 4
|  | Automate unit tests | Developer | Zach, Ian | 1 |  | 1 |  |  |  |  | 0.5 |  | 0.5 | 1
|  | Refactor controllers for testability | Developer | Zach, Ian | 12 |  | 13 |  |  |  |  | 7 |  | 6 | 13
|  | Implement completed data viz | Developer | Wes | 8 |  | 8 | [5 empty] | 8 |  | 8
|  | Finalize notification features | Developer | Ryan, Colin, Jayson | 21 |  | 22 |  | 7.25 | 7.25 | 7.25 |  |  |  | 21.75
| Analysis |  |  |  |  | 8 |  | 9 | [6 empty] | 9
|  | Acceptance Testing | Tester, Project Manager | Zach, Wes | 2 |  | 2 | [5 empty] | 1 | 1 | 2
|  | Bug fix as required | Tester, Developer | Ryan | 6 |  | 7 |  |  |  | 7 |  |  |  | 7
Iteration 4: | Design |  |  |  |  | 18 |  | 18 | [6 empty] | 18
|  | Implement any design changes | Project Manager | Zach, Wes | 2 |  | 2 | [5 empty] | 1 | 1 | 2
|  | Risk analysis | Project Manager | Zach | 2 |  | 2 | [6 empty] | 2 | 2
|  | Comprehensive Security Analysis | Project Manager | Zach | 4 |  | 4 | [6 empty] | 4 | 4
|  | Design revised UI | Develoepr | Zach, Ryan | 6 |  | 6 |  |  |  | 3 |  |  | 3 | 6
|  | Configure Test Automation in Github |  | Zach | 4 |  | 4 | [6 empty] | 4 | 4
| Development |  |  |  |  | 34 |  | 37 | [6 empty] | 37
|  | Add more Unit Tests | Developer | Ian, Zach | 6 |  | 6 |  |  |  |  | 3 |  | 3 | 6
|  | Fine-tune Notifications | Developer | Ryan, Colin Jayson | 18 |  | 21 |  | 7 | 7 | 7 |  |  |  | 21
|  | Data Exporting | Developer | Zach | 4 |  | 4 | [6 empty] | 4 | 4
|  | Emailing Notifications | Developer | Ryan, Colin Jayson | 6 |  | 6 |  | 2 | 2 | 2 |  |  |  | 6
| Analysis |  |  |  |  | 10 |  | 10 | [6 empty] | 10
|  | Acceptance Testing | Tester, Project Manager | Zach, Wes | 2 |  | 2 | [5 empty] | 1 | 1 | 2
|  | Bug fix as required | Tester, Developer | Ryan | 6 |  | 6 |  |  |  | 6 |  |  |  | 6
|  | Evaluate needs for next iteration | Project Manager | Zach, Wes | 2 |  | 2 | [5 empty] | 1 | 1 | 2
Iteration 5: | Design |  |  |  |  | 8 |  | 0 | [6 empty] | 0
|  | Implement any design changes | Project Manager | Zach, Ryan | 2 | [9 empty] | 0
|  | Risk analysis | Project Manager | Zach, Wes | 2 | [9 empty] | 0
|  | Design revised UI | Developer | Zach, Ryan | 4 | [9 empty] | 0
|  |  | Developer | [11 empty] | 0
| Development |  |  |  |  | 22 |  | 0 | [6 empty] | 0
|  | Finalize notifications | Developer | Ryan, Colin, Jayson | 12 | [9 empty] | 0
|  | Data Exporting | Developer | Zach | 4 | [9 empty] | 0
|  | Emailing Notifications | Developer | Ryan, Colin, Jayson | 6 | [9 empty] | 0
|  |  | Developer | [11 empty] | 0
|  |  | Developer | [11 empty] | 0
| Analysis |  |  |  |  | 8 |  | 0 | [6 empty] | 0
|  | Acceptance Testing | Tester, Project Manager | Zach, Wes | 2 | [9 empty] | 0
|  | Bug fix as required | Tester, Developer | Ryan | 6 | [9 empty] | 0
|  | Evaluate needs for next iteration | Project Manager | Wes, Zach | 2 | [9 empty] | 0
Total |  |  |  |  | 251 | 251 | 146.75 | 273.5 | 37.75 | 32.25 | 49.75 | 27 | 42 | 85.5 | 146.75