## Team1_Estimated_Effort
Task Name: (Dependencies top to bottom) | [8 empty] | Colin | Jayson | Ryan | Ian | Wes | Zach | Total
|  |  | Role | Owner | Estimated | Effort | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual
|  |  |  | (primary owner) (secondary owners) | By Task | Subtotals | By Task | Subtotals | By Task | By Task | By Task | By Task | By Task | By Task
Preliminary &
Parallel Tasks | Architecture |  |  |  |  | 12 |  | 10 | [6 empty] | 12
|  | Design architecture | Project Manager | Zach, Wes | 12 |  | 10 | [5 empty] | 6 | 6 | 12
| Requirements |  |  |  |  | 9 |  | 9 | [6 empty] | 9
|  | Gather | Requirements Engineer | Zach, Wes | 2 |  | 2 | [5 empty] | 1 | 1 | 2
|  | Analyze | Requirements Engineer | Zach, Wes | 4 |  | 4 | [5 empty] | 3 | 1 | 4
|  | Specify | Requirements Engineer | Zach, Wes | 3 |  | 3 | [5 empty] | 2 | 1 | 3
| Documentation |  |  |  |  | 28 |  | 28 | [6 empty] | 28
|  | Project Charter | Project Manager | Wes, Zach | 2 |  | 3 | [5 empty] | 2.5 | 0.5 | 3
|  | Release Plan | Project Manager | Zach, Wes | 2 |  | 3 | [5 empty] | 2 | 1 | 3
|  | Requirements Document | Project Manager, Requirements Engineer | Wes, Zach | 5 |  | 6 | [5 empty] | 5 | 1 | 6
|  | Project Plan | Project Manager, Developers | Wes, Zach | 5 |  | 5 | [5 empty] | 3 | 2 | 5
|  | Architecture Document | Architect | Wes, Zach | 4 |  | 4 | [5 empty] | 1 | 3 | 4
|  | Test Report | Tester | Ryan, Ian | 8 |  | 3 |  | 1.5 |  | 1.5 |  |  |  | 3
|  | User Guide & System Admin Doc | Developers, Requirements Engineer | Colin, Ian | 2 |  | 4 |  | 2 |  |  | 2 |  |  | 4
Coding
Iteration 1: | Development |  |  |  |  | 75 |  | 122 | [6 empty] | 0
|  | Determine technology needs | Developer | Everyone :) | 12 |  | 12 |  | 2 | 2 | 2 | 2 | 2 | 2 | 12
|  | Research and learn new language and environment | Developer | Ryan, Colin, Ian | 20 |  | 24 |  | 6 | 6 | 6 | 6 |  |  | 24
|  | Set up azure | Developer | Zach | 10 |  | 4 | [6 empty] | 4 | 4
|  | Write basic azure code | Developer | Zach | 8 |  | 4 | [6 empty] | 4 | 4
|  | Implement classes | Developer | Jayson | 10 |  | 20 |  | 6 | 4 | 10 |  |  |  | 20
|  | Display SSMS information via asp.net | Developer | Colin, Jayson, Ryan | 6 |  | 20 |  | 6 | 6 |  |  |  |  | 12
|  | Data processing | Developer | Ryan | 3 |  | 4 |  |  |  | 4 |  |  |  | 4
|  | Database populated | Developer | Ryan | 3 |  | 10 |  |  |  | 6 |  |  |  | 6
|  | Unit Testing | Developer | Ian, Zach, Ryan | 3 |  | 24 |  |  |  | 5 | 14 |  | 5 | 24
| Analysis |  |  |  |  | 6 |  | 20 | [6 empty] | 0
|  | System Testing | Tester | Jayson, Ian, Colin | 2 |  | 3 |  | 1 | 1 |  | 1 |  |  | 3
|  | Bug fix as required | Tester, Developer | Jayson, Ian, Colin | 2 |  | 15 |  | 5 | 5 |  | 5 |  |  | 15
|  | Evaluate needs for next iteration | Project Manager | Wes, Zach | 2 |  | 2 | [5 empty] | 1 | 1 | 2
Iteration 2: | Design |  |  |  |  | 12 |  | 0 | [6 empty] | 0
|  | Implement any design changes | Project Manager | David, Casey | 2 | [9 empty] | 0
|  | Risk analysis | Project Manager | Casey, David | 2 | [9 empty] | 0
|  | Design XML format | Developer | Cuong, Kyle | 1 | [9 empty] | 0
|  | Design Perl XML-handling code | Developer | Cuong, Kyle | 5 | [9 empty] | 0
|  | Create UI design for balance screen | Developer | Cuong, Kyle | 2 | [9 empty] | 0
| Development |  |  |  |  | 22 |  | 0 | [6 empty] | 0
|  | Review requirements | Developer | Cuong, Kyle | 1 | [9 empty] | 0
|  | Create XML parsing code | Developer | Cuong, Kyle | 5 | [9 empty] | 0
|  | Handle XML data structure for retrieving balance | Developer | Cuong, Kyle | 10 | [9 empty] | 0
|  | Implement UI | Developer | Cuong, Kyle | 4 | [9 empty] | 0
|  | Unit Testing | Developer | Cuong, Kyle | 2 | [9 empty] | 0
| Analysis |  |  |  |  | 6 |  | 0 | [6 empty] | 0
|  | System Testing | Tester | Casey, David | 2 | [9 empty] | 0
|  | Bug fix as required | Tester, Developer | David, Casey, Kyle, Cuong | 2 | [9 empty] | 0
|  | Evaluate needs for next iteration | Project Manager | David, Casey | 2 | [9 empty] | 0
Iteration 3: | Design |  |  |  |  | 22 |  | 0 | [6 empty] | 0
|  | Implement any design changes | Project Manager | David, Casey | 2 | [9 empty] | 0
|  | Risk analysis | Project Manager | Casey, David | 2 | [9 empty] | 0
|  | Create UI design for vendor locations | Developer | Kyle, Cuong | 10 | [9 empty] | 0
|  | Design data structure for RSS location list | Developer | Kyle, Cuong | 8 | [9 empty] | 0
| Development |  |  |  |  | 29 |  | 0 | [6 empty] | 0
|  | Review requirements | Developer | Kyle, Cuong | 1 | [9 empty] | 0
|  | Develop code for processing vendor locations | Developer | Cuong, Kyle | 10 | [9 empty] | 0
|  | Implement vendor map display | Developer | Kyle, Cuong | 8 | [9 empty] | 0
|  | Display vendor information | Developer | Kyle, Cuong | 8 | [9 empty] | 0
|  | Unit Testing | Developer | Kyle, Cuong | 2 | [9 empty] | 0
| Analysis |  |  |  |  | 5 |  | 0 | [6 empty] | 0
|  | Acceptance Testing | Tester, Project Manager | David, Casey | 3 | [9 empty] | 0
|  | Bug fix as required | Tester, Developer | David, Casey, Kyle, Cuong | 2 | [9 empty] | 0
Total |  |  |  |  | 226 | 226 | 118 | 189 | 29.5 | 24 | 34.5 | 30 | 28.5 | 32.5 | 179